# Event Management Plan – A short guide

Further detailed guidance is available through the Purple Guide website for a subscripton of £25 at www.thepurpleguide.co.uk

# 1	Introduction

- What event are you putting on

- Who is involved in the event

Statement acknowledging the Event Management Plan has been prepared to demonstrate the organiser’s commitment to ensure the health, safety and welfare of those who are involved in and attending the event

# 2	Summary of event

- Summary of event

- Date and time

- Location

- How many people do you expect?

- What sort of audience – adults/children/teenagers etc.?

- What sort of behaviour – alcohol/music etc.?

- Will you have food traders?

- Are you providing and special activities, bouncy castle/performance/guest/fireworks etc.?

- Do you need a road closure/traffic restrictions? (Norfolk County Council are the Highway Authority but we may be able to assist with your planning)

# 3	Command structure

- Event Organiser

- Event Manager

- Safety Advisor

- Site Manager

- Trader Manager

- Chief Steward

- Traffic Manager

- First Aid Coordinator

These are typical roles that need to be filled in the organisation of a medium sized event which includes traders and road closures/significant car parking provision. You may need entertainment managers, special effects co-ordinators, security/safeguarding, or other help depending on the event programme. Several of these roles may be carried out by one person.

# 4	Roles and responsibilities

Event Organiser

Ultimate responsibility for the safe running of the event. Establishes the strategic policies that the event operates under and coordinates resources. If duties are delegated, state what and to whom.

Event Manager

Command over the entirety of the event. If duties are delegated, state what and to whom

Safety Advisor

Usually responsible for advising Event Organiser/Manager on management of the event to ensure appropriate safety measures are taken.

- Who

- How qualified/experienced

- When are they available?

Site Manager

Physical management of the site.

- Before the event, list duties – planning use of and preparing site, engaging contractors, checking method statements etc

- On the day of the event, list duties – ensuring site used as planned

- After the event, list duties – clearing and returning site to use

Trader Manager

Liaising with traders.

- Before the event, ensure traders complete the relevant paperwork (risk assessments, safety/training certificates, TENS/Street Trading applications, insurance etc), make traders aware of the rules and procedures that will apply to the event.

- During the event, check traders have what they need, comply with the standards expected and act as trader liaison with site and event managers.

Chief Steward

Management of the Stewards.

- Before the event, decide on how many and where Stewards will be placed, ensure training and information provided and any necessary PPE.

- During the event, check Stewards providing service and take welfare breaks.

- After the event, hold a debriefing to learn lessons from the event.

Traffic Manager

Creating the Traffic Management Plan.

- Before the event, apply for Temporary Traffic Restriction Orders and Road Closures. Decide how many and where Traffic Marshalls placed, ensure they receive training and information on the procedures and any necessary PPE. Arrange pre-event signage of any road closures and restrictions.

- During the event, ensure signage and barriers installed, that the Marshalls provide the service expected and take welfare breaks as necessary.

- After the event, hold a debriefing meeting to learn lessons from the event.

First Aid Coordinator

Ensuring suitable level of first aid provision. You may also wish to consider using the coordinator for safeguarding provisions for children and vulnerable people.

- Before the event, engage a suitable first aid provider and ensure they have the facilities they require.

- During the event, check providing the service expected. Ensure any trends that become apparent during the event are notified to the Safety Advisor/Event Manager as soon as possible.

- After the event, hold a debriefing meeting to learn lessons from the event.

# 5	Event schedule

Set down clearly who does what, and when.

Pre event

Road closure, barrier erection, build, load in

Provision of equipment, electrical rigging, siting of first aid hub, signage, parking provision, staff training

Event

Site management, crowd management, performer management, incident management, facilities management and support services

Post Event

Public clearance, load out, breakdown, barrier removal, road opening, waste collection, receive debriefs

# 6	Event Control

Event Control

- Where is it - location

- Who is in it – who will be based here eg police, fire, ambulance

- What facilities are there

- Opening times

- Closing times

- Contact details

# 7	Site considerations

Site plan, description of site.

- Layout – maps showing site layout, transport routes, storage areas, car parking provision, welfare facilities, water distribution and dispensing etc.

- Temporary structures – marquees/stages/inflatables

- Fire safety

- Electrical safety

- Gas safety

- Car parking

- Security

# 8	Crowd management

- Capacity management

- Crowd make up

- Entrances and exits

- Safety Barriers

- Signage

# 9	Stewards

- How many

- Who

- What training have they had

- Are they DBS checked.

- Steward organisation

- Steward duties

- Steward training and site induction processes

- Steward welfare

# 10	First aid provision

Nearest Minor Injuries Unit and nearest A&E

- How many first aiders

- Where are they based

- Communications

- Welfare

- Clinical waste management

- Trend identification and report

# 11	Welfare facilities

- Sanitary facilities – numbers in line with Purple Guide, provision and restocking

- Drinking water

- Lost children – where to meet, how to alert stewards, where to hold child, procedure for returning to parent

- Anti-social behaviour

# 12 	Communications

- Phone/radio use

- Mobile phones – not to be relied upon as in emergency signal will go

- PA system?

- Landline at event control

- Pre event briefings

- Emergency announcements

# 13	Trader issues

- Pre event documentation – food hygiene training/gas safety certificates/Food Hygiene Rating Scheme score (minimum of 3)/risk assessments

- Vehicle safety – movement restrictions before, during and after event

- Alcohol licensing

- Water supply

- Power provision (discourage petrol generators)

- LPG storage and use

- Waste disposal for traders

- Waste water disposal

# 14	Traffic Plan

Vehicle movements on site

## Restrictions on movement

## Provision for emergency vehicles

Traffic Management Plan

## How many people, how are they likely to travel to the event

## Plan of local road network, ingress and exit routes

## Map of road closure, show signage points, diversion routes, and stewarding positions

## Public transport information, include waking and cycling routes

## TTRO road closures, clearways, one way routes, parking suspension

## Emergency vehicle routes

Car parking

## Car pakring deaitls

## Capacities

## Overflow parking provisions

## Park and ride?

- Marshals – how many, where, welfare issues/requirements, no interaction near highway

- Segregation from pedestrians

- Signage

- Weather issues

# 15	Incident / Emergency Control

- General procedures – informing event control

- Who determines appropriate course of action

- Logging arrangements

- Alerting staff to heightened state of readiness

- Handover of control if necessary

- Evacuation procedures

- Access for emergency vehicles

- Weather contingency – heat/wet/wind

- Terrorist precautions/bomb threats

# 16	Waste management

- Cleansing facilities and staff

- Public areas

- Toilets

- Waste disposal from site

# 17	Other Issues that need detailing

- Camping?

- Private water supply?

- Entertainment?

- Fireworks?

- Site structure, marquees, inflatables and fairground rides

# 18	Contacts list

Please include a contacts list of all event staff and volunteers, stating their role, name, and contact number on the day of the event.

# 19	Review

- A debrief will be held on ….

- What the debrief will include

- Learning points

- First plans for next event

# 20 	Risk assessments

- General risk assessment covering the site hazards, crowd hazards, vehicle hazards etc

- Specific risks such as fireworks, bouncy castles, animal petting/contact, water activities etc

- Fire risk assessment

- Weather contingency, heat, wind, rain